## traditional
2008/2009 COMMON CALENDAR |  |  | STUDENT FISCAL SERVICES, FINANCIAL AID, REGISTRAR, AIS
OFC | SCREEN | ACTIVITY | DEPENDENCY | GENERIC | SUM 2008 | AUT 2008 | WIN 2009 | SPR 2009
REG | -- | initial grade posting for prior quarter |  | Mon. or Tues. after end of prior qtr | 2008-06-16 | 2008-08-25 | 2008-12-16 | 2009-03-23
FAO | -- | academic progress | > posting grades | Between grades & account setup | 2008-06-17 | 2008-08-26 | 2008-12-29 | 2009-03-24
SFS |  | first direct loan draw down |  | Same as account setup | 2008-06-18 | 2008-08-27 | 2008-12-30 | 2009-03-25
SFS | SAU901 | Initial Account Setup | > acad progress, no more than 10 days before 1st day | 5 days before 1st day of quarter | 2008-06-18 | 09/17/08 - 08/27/08 - med | 2008-12-30 | 2009-03-25
SFS | SAP990 | 1st ACH filed created - sent next business day |  | Same as account setup | 2008-06-18 | 2008-09-17 | 2008-12-30 | 2009-03-25
SFS | SAP990 | housing process |  | The day before account setup (not summer) | TBD | TBD | TBD | TBD
SFS | SAP990 | UWEO process |  | The day before account setup | TBD | TBD | TBD | TBD
SFS | SAU220 | Departmental charges added to be paid by aid | added by departments | Before 1st ACH file | By 6/18/08 | By 9/17/2008 | By 12/30/08 | By 3/25/09
REG | -- | 1st day process |  | 2 working days prior to the start of qtr | 2008-06-19 | 2008-09-22 | 2008-12-31 | 2009-03-26
FAO |  | 1st day to apply for STL for upcoming qtr |  | Day after account set-up | 2008-06-19 | 2008-09-18 | 2008-12-31 | 2009-03-26
REG | SRF720 | 1st day of quarter |  |  | F&A: 6/23/08 B: 7/24/08 | 09/24/08 - 09/02/08 - med | 2009-01-05 | 2009-03-30
SFS | SAU901 | 1st day for 1st late registration fee |  | see Academic Calendar | F&A: 6/23/08 B: 7/24/08 | 2008-09-24 | 2009-01-05 | 2009-03-30
REG | -- | prev qtr low scholarship cancellation |  | 3rd day of qtr | 2008-06-25 | 2008-09-26 | 2009-01-07 | 2009-04-01
SFS |  | last day to change insurance |  | 7th calendar day of qtr | 2008-06-29 | 2008-09-30 | 2009-01-11 | 2009-04-05
SFS | SAU901 | 50% forfeiture of tuition |  | 8th - 30th calendar days of qtr - (Sum) : 8th-21st | F&A: 6/30- 7/13/08 B: 7/31- 8/13/08 | 10/01/08-10/23/08 | 1/12/09-2/3/09 | 4/6/09-4/28/09
SFS | SAU901 | 1st day for $20 course change fee |  | 8th calendar day of qtr | F&A: 6/30 B: 7/31 | 2008-10-01 | 2009-01-12 | 2009-04-06
REG |  | Census Day | Between 1st&2nd late registration | 2nd Friday of qtr | 2008-07-03 | 2008-10-03 | 2009-01-16 | 2009-04-10
SFS | SAU901 | 1st day for 2nd late registration fee |  | see Academic Calendar (15th calendar day of qtr - except Sum B term) | F&A: 7/07 B: 7/31 | 2008-10-08 | 2009-01-19 | 2009-04-13
REG |  | last day to add/register for classes |  | see Academic Calendar (21st calendar day of qtr - except Sum B term) | F&A: 7/13 B: 7/30 | 2008-10-14 | 2009-01-25 | 2009-04-19
SFS | SAU901 | Tuition Due Date |  | 3rd friday of qtr | 2008-07-11 | 2008-10-10 | 2009-01-23 | 2009-04-17
SFS | SAU902 | late payment fees added |  | Tuesday after due date | 2008-07-15 | 2008-10-14 | 2009-01-27 | 2009-04-21
SFS |  | insurance file created |  | 2nd Friday 4th Friday and last day of quarter | 7/7 7/18 8/22 | 10/3 10/17 12/12 | 1/16 1/30 3/20 | 4/10 4/24 6/12
SFS | SAU901 | 100% forfeiture of tuition |  | Day after 30th calendar day (except Summer) | F&A: 7/14 B: 8/14 | 2008-10-24 | 2009-02-04 | 2009-04-29
SFS | SAP990 | Holds (non-payment) | B/4 registration for next quarter (except Summer) | Day after 30th calendar day (except Summer) | 2008-07-14 | 2008-10-24 | 2009-02-04 | 2009-04-29
REG | SRF722 | 1st day of next quarter registration |  | See academic calendar |  | 2008-11-07 | 2009-02-20 | 5/2/08-Aut 4/20/09-Sum
REG | SRF720 | last day to drop classes |  | Sunday of 8th week of qtr (except Summer) | F: 8/10 A: 7/13 B: 8/13 | 2008-11-09 | 2009-02-22 | 2009-05-17
REG | -- | Print faculty grade reports | after last day to drop | 8thThursday of qtr (except Summer) | A: 7/15 B: 8/14 | 2008-11-13 | 2009-02-26 | 2009-05-21
REG | SRF720 | Last day of quarter |  | See academic calendar | 2007-08-22 | 2008-12-12 | 2009-03-20 | 2009-06-12
SFS |  | prior year direct loan cut off |  | 180 days after last day of spring qtr |  |  |  | 2009-12-09
| -- | · printing prior year notes |  | last day of quarter |  |  |  | 2009-06-12
| -- | · disbursing prior year funds |  | 180 days after end of spring qtr |  |  |  | 2009-12-09
FAO/SFS | -- | Financial purge |  |  | report only 8/21/08 actual 8/28/08
REG |  | Admissions purge | after last day to register | 4th Friday of qtr (Sum. 6th Friday) | 2008-08-01 | 2008-10-17 | 2009-01-30 | 2009-04-24
SFS |  | Extended disbursement date |  | 2 days B/4 account setup for next qtr | 2008-08-25 | 2008-12-26 | 2009-03-23 | 2009-06-15
SFS |  | Annual budgets & charges rollover |  | 1st Friday in December |  |  | 2009-02-01

## by date
2008/2009 COMMON CALENDAR |  |  | STUDENT FISCAL SERVICES, FINANCIAL AID, REGISTRAR, AIS
OFC | SCREEN | ACTIVITY | DEPENDENCY | GENERIC | SUM 2008 | AUT 2008 | WIN 2009 | SPR 2009
REG | -- | initial grade posting for prior quarter |  | Mon. or Tues. after end of prior qtr | 2008-06-16 | 2008-08-25 | 2008-12-16 | 2009-03-23
FAO | -- | academic progress | > posting grades | Between grades & account setup | 2008-06-17 | 2008-08-26 | 2008-12-29 | 2009-03-24
SFS |  | first direct loan draw down |  | Same as account setup | 2008-06-18 | 2008-08-27 | 2008-12-30 | 2009-03-25
SFS | SAU901 | Initial Account Setup | > acad progress, no more than 10 days before 1st day | 5 days before 1st day of quarter | 2008-06-18 | 09/17/08 - 08/27/08 - med | 2008-12-30 | 2009-03-25
SFS | SAP990 | 1st ACH filed created - sent next business day |  | Same as account setup | 2008-06-18 | 2008-09-17 | 2008-12-30 | 2009-03-25
SFS | SAP990 | housing process |  | The day before account setup (not summer) | TBD | TBD | TBD | TBD
SFS | SAP990 | UWEO process |  | The day before account setup | TBD | TBD | TBD | TBD
SFS | SAU220 | Departmental charges added to be paid by aid | added by departments | Before 1st ACH file | By 6/18/08 | By 9/17/2008 | By 12/30/08 | By 3/25/09
REG | -- | 1st day process |  | 2 working days prior to the start of qtr | 2008-06-19 | 2008-09-22 | 2008-12-31 | 2009-03-26
FAO |  | 1st day to apply for STL for upcoming qtr |  | Day after account set-up | 2008-06-19 | 2008-09-18 | 2008-12-31 | 2009-03-26
REG | SRF720 | 1st day of quarter |  |  | F&A: 6/23/08 B: 7/24/08 | 09/24/08 - 09/02/08 - med | 2009-01-05 | 2009-03-30
SFS | SAU901 | 1st day for 1st late registration fee |  | see Academic Calendar | F&A: 6/23/08 B: 7/24/08 | 2008-09-24 | 2009-01-05 | 2009-03-30
REG | -- | prev qtr low scholarship cancellation |  | 3rd day of qtr | 2008-06-25 | 2008-09-26 | 2009-01-07 | 2009-04-01
SFS |  | last day to change insurance |  | 7th calendar day of qtr | 2008-06-29 | 2008-09-30 | 2009-01-11 | 2009-04-05
SFS | SAU901 | 50% forfeiture of tuition |  | 8th - 30th calendar days of qtr - (Sum) : 8th-21st | F&A: 6/30- 7/13/08 B: 7/31- 8/13/08 | 10/01/08-10/23/08 | 1/12/09-2/3/09 | 4/6/09-4/28/09
SFS | SAU901 | 1st day for $20 course change fee |  | 8th calendar day of qtr | F&A: 6/30 B: 7/31 | 2008-10-01 | 2009-01-12 | 2009-04-06
REG |  | Census Day | Between 1st&2nd late registration | 2nd Friday of qtr | 2008-07-03 | 2008-10-03 | 2009-01-16 | 2009-04-10
SFS |  | insurance file created |  | 2nd Friday 4th Friday and last day of quarter | 7/7 7/18 8/22 | 10/3 10/17 12/12 | 1/16 1/30 3/20 | 4/10 4/24 6/12
SFS | SAU901 | 1st day for 2nd late registration fee |  | see Academic Calendar (15th calendar day of qtr - except Sum B term) | F&A: 7/07 B: 7/31 | 2008-10-08 | 2009-01-19 | 2009-04-13
REG |  | last day to add/register for classes |  | see Academic Calendar (21st calendar day of qtr - except Sum B term) | F&A: 7/13 B: 7/30 | 2008-10-14 | 2009-01-25 | 2009-04-19
SFS | SAU901 | Tuition Due Date |  | 3rd friday of qtr | 2008-07-11 | 2008-10-10 | 2009-01-23 | 2009-04-17
SFS | SAU902 | late payment fees added |  | Tuesday after due date | 2008-07-15 | 2008-10-14 | 2009-01-27 | 2009-04-21
SFS | SAU901 | 100% forfeiture of tuition |  | Day after 30th calendar day (except Summer) | F&A: 7/14 B: 8/14 | 2008-10-24 | 2009-02-04 | 2009-04-29
SFS | SAP990 | Holds (non-payment) | B/4 registration for next quarter (except Summer) | Day after 30th calendar day (except Summer) | 2008-07-14 | 2008-10-24 | 2009-02-04 | 2009-04-29
REG | SRF722 | 1st day of next quarter registration |  | See academic calendar |  | 2008-11-07 | 2009-02-20 | 5/2/08-Aut 4/20/09-Sum
REG | SRF720 | last day to drop classes |  | Sunday of 8th week of qtr (except Summer) | F: 8/10 A: 7/13 B: 8/13 | 2008-11-09 | 2009-02-22 | 2009-05-17
REG | -- | Print faculty grade reports | after last day to drop | 8thThursday of qtr (except Summer) | A: 7/15 B: 8/14 | 2008-11-13 | 2009-02-26 | 2009-05-21
REG | SRF720 | Last day of quarter |  | See academic calendar | 2007-08-22 | 2008-12-12 | 2009-03-20 | 2009-06-12
SFS |  | prior year direct loan cut off |  | 180 days after last day of spring qtr |  |  |  | 2009-12-09
| -- | · printing prior year notes |  | last day of quarter |  |  |  | 2009-06-12
| -- | · disbursing prior year funds |  | 180 days after end of spring qtr |  |  |  | 2009-12-09
REG |  | Admissions purge | after last day to register | 4th Friday of qtr (Sum. 6th Friday) | 2008-08-01 | 2008-10-17 | 2009-01-30 | 2009-04-24
SFS |  | Annual budgets & charges rollover |  | 1st Friday in December |  |  | 2009-02-01
FAO/SFS | -- | Financial purge |  |  | report only 8/21/08 actual 8/28/08
SFS |  | Extended disbursement date |  | 2 days B/4 account setup for next qtr | 2008-08-25 | 2008-12-26 | 2009-03-23 | 2009-06-15

## by office
2008/2009 COMMON CALENDAR |  |  | STUDENT FISCAL SERVICES, FINANCIAL AID, REGISTRAR, AIS
OFC | SCREEN | ACTIVITY | DEPENDENCY | GENERIC | SUM 2008 | AUT 2008 | WIN 2009 | SPR 2009
FAO | -- | academic progress | > posting grades | Between grades & account setup | 2008-06-17 | 2008-08-26 | 2008-12-29 | 2009-03-24
FAO |  | 1st day to apply for STL for upcoming qtr |  | Day after account set-up | 2008-06-19 | 2008-09-18 | 2008-12-31 | 2009-03-26
FAO/SFS | -- | Financial purge |  |  | report only 8/21/08 actual 8/28/08
REG | -- | initial grade posting for prior quarter |  | Mon. or Tues. after end of prior qtr | 2008-06-16 | 2008-08-25 | 2008-12-16 | 2009-03-23
REG | -- | 1st day process |  | 2 working days prior to the start of qtr | 2008-06-19 | 2008-09-22 | 2008-12-31 | 2009-03-26
REG | SRF720 | 1st day of quarter |  |  | F&A: 6/23/08 B: 7/24/08 | 09/24/08 - 09/02/08 - med | 2009-01-05 | 2009-03-30
REG | -- | prev qtr low scholarship cancellation |  | 3rd day of qtr | 2008-06-25 | 2008-09-26 | 2009-01-07 | 2009-04-01
REG |  | Census Day | Between 1st&2nd late registration | 2nd Friday of qtr | 2008-07-03 | 2008-10-03 | 2009-01-16 | 2009-04-10
REG |  | last day to add/register for classes |  | see Academic Calendar (21st calendar day of qtr - except Sum B term) | F&A: 7/13 B: 7/30 | 2008-10-14 | 2009-01-25 | 2009-04-19
REG | SRF722 | 1st day of next quarter registration |  | See academic calendar |  | 2008-11-07 | 2009-02-20 | 5/2/08-Aut 4/20/09-Sum
REG | SRF720 | last day to drop classes |  | Sunday of 8th week of qtr (except Summer) | F: 8/10 A: 7/13 B: 8/13 | 2008-11-09 | 2009-02-22 | 2009-05-17
REG | -- | Print faculty grade reports | after last day to drop | 8thThursday of qtr (except Summer) | A: 7/15 B: 8/14 | 2008-11-13 | 2009-02-26 | 2009-05-21
REG | SRF720 | Last day of quarter |  | See academic calendar | 2007-08-22 | 2008-12-12 | 2009-03-20 | 2009-06-12
REG |  | Admissions purge | after last day to register | 4th Friday of qtr (Sum. 6th Friday) | 2008-08-01 | 2008-10-17 | 2009-01-30 | 2009-04-24
SFS |  | first direct loan draw down |  | Same as account setup | 2008-06-18 | 2008-08-27 | 2008-12-30 | 2009-03-25
SFS | SAU901 | Initial Account Setup | > acad progress, no more than 10 days before 1st day | 5 days before 1st day of quarter | 2008-06-18 | 09/17/08 - 08/27/08 - med | 2008-12-30 | 2009-03-25
SFS | SAP990 | 1st ACH filed created - sent next business day |  | Same as account setup | 2008-06-18 | 2008-09-17 | 2008-12-30 | 2009-03-25
SFS | SAP990 | housing process |  | The day before account setup (not summer) | TBD | TBD | TBD | TBD
SFS | SAP990 | UWEO process |  | The day before account setup | TBD | TBD | TBD | TBD
SFS | SAU220 | Departmental charges added to be paid by aid | added by departments | Before 1st ACH file | By 6/18/08 | By 9/17/2008 | By 12/30/08 | By 3/25/09
SFS | SAU901 | 1st day for 1st late registration fee |  | see Academic Calendar | F&A: 6/23/08 B: 7/24/08 | 2008-09-24 | 2009-01-05 | 2009-03-30
SFS |  | last day to change insurance |  | 7th calendar day of qtr | 2008-06-29 | 2008-09-30 | 2009-01-11 | 2009-04-05
SFS | SAU901 | 50% forfeiture of tuition |  | 8th - 30th calendar days of qtr - (Sum) : 8th-21st | F&A: 6/30- 7/13/08 B: 7/31- 8/13/08 | 10/01/08-10/23/08 | 1/12/09-2/3/09 | 4/6/09-4/28/09
SFS | SAU901 | 1st day for $20 course change fee |  | 8th calendar day of qtr | F&A: 6/30 B: 7/31 | 2008-10-01 | 2009-01-12 | 2009-04-06
SFS | SAU901 | 1st day for 2nd late registration fee |  | see Academic Calendar (15th calendar day of qtr - except Sum B term) | F&A: 7/07 B: 7/31 | 2008-10-08 | 2009-01-19 | 2009-04-13
SFS | SAU901 | Tuition Due Date |  | 3rd friday of qtr | 2008-07-11 | 2008-10-10 | 2009-01-23 | 2009-04-17
SFS | SAU902 | late payment fees added |  | Tuesday after due date | 2008-07-15 | 2008-10-14 | 2009-01-27 | 2009-04-21
SFS |  | insurance file created |  | 2nd Friday 4th Friday and last day of quarter | 7/7 7/18 8/22 | 10/3 10/17 12/12 | 1/16 1/30 3/20 | 4/10 4/24 6/12
SFS | SAU901 | 100% forfeiture of tuition |  | Day after 30th calendar day (except Summer) | F&A: 7/14 B: 8/14 | 2008-10-24 | 2009-02-04 | 2009-04-29
SFS | SAP990 | Holds (non-payment) | B/4 registration for next quarter (except Summer) | Day after 30th calendar day (except Summer) | 2008-07-14 | 2008-10-24 | 2009-02-04 | 2009-04-29
SFS |  | prior year direct loan cut off |  | 180 days after last day of spring qtr |  |  |  | 2009-12-09
SFS |  | Extended disbursement date |  | 2 days B/4 account setup for next qtr | 2008-08-25 | 2008-12-26 | 2009-03-23 | 2009-06-15
SFS |  | Annual budgets & charges rollover |  | 1st Friday in December |  |  | 2009-02-01
| -- | · printing prior year notes |  | last day of quarter |  |  |  | 2009-06-12
| -- | · disbursing prior year funds |  | 180 days after end of spring qtr |  |  |  | 2009-12-09